## SPEC
| Units | Description | VLSI Owner | RTL Ready | Port Freeze | RTL Freeze | Note | PM notes
CHIP ID | chip id | 96(0x60) for MS1 | liang.zhao
Part Number
Segment | Which AML product line | MS1
TO date | 2025-09-30
CB date
MP date
Package | Package Type | BGA
Metal Stack | FC/WB, layers | 1P 7M?
Process | Geometry, Process | T22ULL
| Memory Configuration |  | / | / | / | /
| Memory Compression |  | / | / | / | /
| Internal RAM(OCRAM) | 64KB 16KB on chip AHB_SRAM | boyuan.xu/liang.zhao | Y
| Share_Ram (axi_sram) | 2MB？axi_sram | boyuan.xu/chao.gao | Y |  |  | 32bit bus, 500MHz timing opt | 5/19：已经commit in,Size确定2MB，本周确认是否Share;
| ROM | no ROM for BOOT | / | / | / | /
Video Interface | HDMI2.1 RX | TMDS 6G Support HDMI2.1 VRR HDCP 1.4/2.2/2.3 | zekun.ma | Y |  |  | DDC channel, I2C host & slave mode for external e2prom read/write and DDC communication HDMI-0 programable I2C/UART for debug, SW download and debug information print | 5/19：已放入tree
| DP1.4 RX | Support 8.1Gbps/5.4Gbps/2.7Gbps/1.62Gbps per lane Support no link training/fast link training/full link training SST mode, HDCP 1.4/2.2/2.3 | bo.li | Y |  |  | DDC/AUX in AO domain GPIO for cable detect (no FEC) | 5/19：已放入tree
| VGA RX | hsync/vsync detect | chao.gao | Y |  |  | 画面的自动调整： 所有的分辨率正常显示，(通常在低分辨率会有问题？) 端口兼容性：表现出来是黑屏 水波纹的干扰：应该是模拟端的处理 数字端要做低通滤波： | VGA：确认会放入，下周前有面積評估
| LVDS TX | 4 ports 8b LVDS clock up to 175MHz 2 ports share 1 pairs clock Flexible spread spectrum to reduce EMI Support pair swap and P/N swap | guojin/chao.gao | Y |  |  |  | 5/19:已放入
| eDP1.2 TX | 8lane up to HBR2 5.4G output 1Mbps AUX channel , no HDCP, no AUDIO | yulong.lian | Y |  |  | (no FEC, no PSR) QHD200 need 8lane HBR2 ，should two eDP controller | 5/19：已放入tree
| RX HDCP2.x | HDMI/DP shared HDCP1.4/2.2/2.3 auth | gangying.yin | Y |  |  | 安全性要求不高， HDCP key 加密后放入flash，硬件解密
| HDCP AES |  | gangying.yin | Y |  |  | 增加软件解密的部分，可以直接送裸key到数字
| video_out top |  | chao.gao | Y |  |  |  | 6/9:持续优化
| Video_in top |  | kai.Sun | Y |  |  |  | 5/26:已放入video in
| Video_in AO |  | kai.Sun | Y |  |  |  | 6/9：持续优化
Analog | HDMIRx/DPRx combo phy | port0:hdmi; port1: hdmi/dp combo; port2: dp | wei.zhong/knight | / | / | / | DP for HBR3/2
| LVDS_Tx/eDP_Tx combo phy | eDP 5.4G | jinguo/knight | / | / | / | eDP支持8lane, lvds 2port only; lvds/dep 2port comb
| VGA | 10b triple channel ADC 205MHz 2048*1152@60Hz Support H/V Sync, no need SOG Auto input signal format detection, all VESA standard Auto turning include positioning, offset etc | Harry.zhu/knight | / | / | / |  | VGA：需要专题讨论，
| PLL |  | chandle.zou/knight | / | / | /
| POR | 3.3v | yongbing.li/knight | / | / | /
| LVR | 0.9v | yongbing.li/knight | / | / | /
| ESD/IO |  | da.cheng/knight | / | / | /
| TempSensor/others | ts_top | knight | / | / | /
Audio Interface | DAC(analog) | Line Output SNR: 95dB (A-Weighted), THDN:-80dB@-3dBFS Audio DAC support 8~192kHz sample rates | Harry.zhu/knight |  |  |  | Built-in 2 channel audio DAC and Earphone Amp(20mW@32ohm) L/R line out and L/R Earphone out separately and L/R independent swap (Line out, Earphone 可以同时用，出2套pin)
| Earphone AMP(analog) | 20mW@32ohm | Harry.zhu/knight
| Audio process | I2S/SPDIF, Fade in/out; Mute; Volume > 100steps resample | boyuan.xu | Y |  |  | I2S/SPDIF digital pin share with line & earphone out I2S clock keep on when disbale hdmirx, spidif no issue | 6/3:更新的已放入； 5/26: 已放入video in ，本周放入a codec； 5/19：本周再次放进去一版；
Display Processing | Retiming | 6* linebuffer? | chao.gao | Y |  |  |  | 6/9：持续优化
| Scaler | fully programmble scaling ratio; hscaler 2/4/8 taps; vscaler 2/4 taps, 4x linebuffer | ruixin.wang/xianjun | Y |  |  | 对比其他monitor，确定tap数和linebuffer | 6/9:持续优化； 5/26：OSD 略有delay， 5/19:Display 这部分计划月底放进去，前提是算法不再修改；
| HDR10 | 算法需要简化 | jialu.wang/xianjun | Y |  |  | CTA-861 static metadata
| Sharpness | 算法需要简化 | xuping.shen/xianjun | Y
| Global contrast |  | xuping.shen/xianjun | Y
| Local contrast |  | xuping.shen/xianjun | Y |  |  | 7/10:guoping沟通算法讨论-tao.ji
| CM (color management) |  | linqing.zhu/xianjun | Y
| CSC | RGB2YUV, YUV2RGB | linqing.zhu/xianjun | Y
| VADJ | sRGB/xvYCC | linqing.zhu/xianjun | Y
| 3D LUT | 9x9x9 | linqing.zhu/xianjun | Y
| Gamma | 12bit RGB gamma CLUT | linqing.zhu/xianjun | Y |  |  | support VRR ?
| Luma-hist |  | linqing.zhu/xianjun | Y
| OD | frame buffer: 2MB; compress ratio 6 | yujie/chao.gao | Y |  |  | support VRR ? 临时作为OSD buffer
| BCON | 1152 zones (48x24), 4lane,12gpio | pengcong/chao.gao | Y |  |  | Embed LDC BCON 4 lanes, including HYASIC, X-Signal, XIANXIN etc. protocol
| OSD | . Embedded 48KB SRAM dynamically stores OSD index and fonts . Support 1/2/4 bit/pixel OSD font, font size 12*18, 64 color palette . Support 8 OSD windows, draw lines and rectangle with gradient color . 256 level alpha blending of video, rectangular and OSD windows . Support OSD Top-bottom flip, left-right mirror and 90/270 rotate . Draw OSD in temp. area, Copy to OSD space within v-blank, Display next frame | wenqiang.ge/xianjun | Y
| Statics | VESA DisplayHDR400测试需要动态背光功能，需要硬件统计 (1) 整个画面的平均亮度 --> 用于动态背光调整 (2) 整个画面最亮点的值 --> 在全黑的背景下，如果有光标，需要把背光点起来 (3)任意位置画一个窗口，最大128x128，求RGB均值 --> 应用在游戏时画准星（OSD画，在屏幕正中心），也可以用来检测图像边界 | xianjun | Y |  |  | System function
| Dither | 10to8;8to6 | chao.gao | Y
| VRR | Support AMD Free-sync and Nvidia G-sync compatible | linqing.zhu/xianjun | Y
| MPRT | Support VRR; pwm output | chao.gao | Y |  |  | Moving Picture Response Time | 5/19：已经commit in
| LDC | 1152 zones (max 48x24) | liqiang.ma/xianjun | Y |  |  | 1152=48x24 需要确认sram的size？ | 6/9：持续优化； 5/19:Display 这部分计划月底放进去，前提是算法不再修改；
| VPU_TOP |  | xianjun | Y
CPU and Peripheral | AOCPU(RISCV 32bit) | 400Mhz, ICACHE 16KB, No ILM 64KB ILM | jian.liao/liang.zhao | Y |  |  | new N205 package(v2.10.0) 64KB ILM，16KB ICACHE
| SPIFC(XIP-QSPI) | Quad SPI flash interface clock up to 100MHz, flash size up to 16MB Nor flash support XIP | jian.liao | Y |  |  | MS1 1MB or 2MB cpu xip ahb read，fast read, dual read,quad read cpu/i2c_debug program flash
| SPI_SG | x1 for LDC, | shuwang.qin | Y |  |  | MISO/MOSI/CLK/CS 标准4根线 可以支持一根data线全双工，两线data半双工
| UART | UART0(AO domian) for debug, pin shared to HDMI I2C UART1(EE domain) for others | jian.liao | Y
| I2C | I2c_debug for debug/upgrade, AO domain | jian.liao | Y |  |  | 1. 通过I2C_DBEUG外部能够访问全局memory map 2. 上位机通过hdmi0/1 ddc 通道烧录软件到flash(空片+cpu code crash均能通过debug_i2c控制) 3. Add Access password check(需要输入准确的pwd才能访问memmap) 4. 支持停住cpu
|  | HDMI0/1 I2C(DDC) | zekun.ma/kai.sun | Y |  |  | 1. hdmi0/1 i2c pin需要pinmux到uart
|  | i2c_m/s x2(t6x new version support both mst&slv, both at EE domiain for e2prom & external deivce) | shuwang.qin | Y |  |  | 1. i2c m/s(master mode)可以通过hdmi ddc 通道配置外部eeprom
|  | I2C_M/S x1 @AO for MCCS |  | Y |  |  | 1. new add I2C for MCCS Slave 2. pin通过 HDMIRX ddc 0/1 pin和dp aux module port 3. pinmux不体现，RTL中和ddc i2c/dp share pin
| PWM | pwm_a/b/c/d(AO domain) pwm_e/f/g/h(EE domain) | jian.liao | Y
| SAR ADC | 4 channel， AO domain（standby 可以不用响应 SAR ADC，换成power key gpio） | boyuan.xu/tao.hu analog: harry.zhu | Y |  |  | saradc可以放在EE domain，standby 可以不用响应 SAR ADC，通过power key gpio | 5/26:放入EE domain； 5/19:确认放置AO domain, EE domain
| IR_RX | IR_RX(AO domian), 1路Rx | jian.liao | Y |  |  | 保留IR Rx硬件检测模块。软件方案：detect GPIO, SW decode GPIO边沿中断+timer
| USB2.0 DRD | usb2.0 h, for SW upgrade | digital: lu.han/zheng.zhou analog phy: wei.zhong | Y |  |  | Syno vendor IP | 5/26：已放入 5/19:本周放置DRD
SoC TOP/Others | Timer | timerA x1, timerE x1 | jian.liao | Y
| WDT | WatchDog *1 at reset_ctrl | jian.liao | Y
| memory | TSMC 22nm memory wrapper/model/database | tao.hu/xiaoyong.ma | / | / | / |  | 5/19:VPU/AO memory OK,
| pinmux(GPIO) | ao+ee | jian.liao/liang.zhao | Y |  |  | gpio 3.3v only, device 2.5v acodec & vga analog share 数字IO | 5/26:6月初定pinmux; 5/19:本周讨论pin mux
| bus | ahb matrix arb/dec, apb decoder,nic_ee | liang.zhao/faying.luo | Y |  |  |  | 5/26:本周更新进去 5/19:本周ready
| clk_ctrl | ao+ee | jian.liao/liang.zhao | Y |  |  |  | 5/26：初版已有，还在修改； 5/19:EE domain, clk requirement确认后，完善 Ctrl
| reset_ctrl | ao, cost down | jian.liao | Y |  |  |  | 5/19:EE domain, clk requirement确认后，完善 Ctrl
| irq_ctrl | gpio irq AO: 4; EE:4 | jian.liao/liang.zhao | Y
| maibox | NA | / | / | / | / | / | /
| power_ctrl | mem_pd update&costdown | liang.zhao/jian.liao/wenhao | Y |  |  | Standby chip功耗要求<0.05w, 芯片区分always on domain和main(EE) domain, CPU处于always on domain, standby时降频工作 RX HDMI DDC和DP AUX接口和Power key需要在always on domain, 用于standby唤醒 | 5/26： 5/19:待Power domain讨论结果;
| JTAG(pinmux) | for N205 RISCV debug | jian.liao | Y |  |  | gpio pinmux n205 jtag access | 5/26:6月初有初版 5/19:本周讨论pin mux
| DFT | scan/mbist/analog FT | feng.hu/jian.liao | Y |  |  |  | 6/3：已和BE tiger聊过，邮件已发； 5/19:DFT待完善，与BE DFT owner 再确认
| osc_ring |  | jian.liao | Y |  |  |  | 6/3：待面积初步确定后更新； 5/26：本周scan/osc ring同步讨论； 5/19:待与BE讨论，本周有初步讨论结果
| temp_sensor | top only | jian.liao | Y |  |  |  | 5/19:已放入 tree;
| analog_intergration | analog model/lib, pll, misc... | xiaoyong.ma/tao.hu
| eFuse | efuse_ctrl | tao.hu | Y |  |  | 最小size efuse 16x32=512bit Analog calibration 64bit MKT需求12bytes: - Unique ID 4bytes; 加密 UID’ 4bytes, 用于防抄板保护(copy protection, custom area) - 芯片硬件功能区分 2bytes, 包括LDC，pixel clock, TX eDP等 - 芯片软件区分 2bytes, 客户和功能软件区分 | 5/19:待会议讨论的Items close；
SW | RTOS |  | guoping.li | / | / | / | 暂无更新
| PQ |  | guoping.li | / | / | / | time cost in AOCPU@166MHz (no I/D cache) >LDC （48*24 = 1152 region） : 7000 uS (1572+2784+2784) >LDC memory : 35K Bytes (友商大约11K Bytes) https://confluence.amlogic.com/display/SW/LDC+algorithm+in+aocpu+performance 1. 目前经过讨论，local dimming如果mapping调整为Hardware来做，后面协议转换，采用ping-pang buffer, 可以从7ms优化到0ms, 完全采用hardware来做，软件保留中断，作为未来面临特殊协议的时候，workarround。 2. 希望提供一个DMA, 用于memcpy优化。
| OSD |  | guoping.li | / | / | / | 1. 希望能提供 shaddow register功能, 使用场景 > SetupPath > Set Scaling Filter/Factor >OSD set position > supper resolution > PQ set RGB gain / EnableY2RMatrix
| Video input |  | guoping.li | / | / | /
| USB upgrade |  | guoping.li | / | / | /
| 产线工具 |  | guoping.li | / | / | /
FPGA |  |  | chuyin.wang/junjie.sun/chao.gao | / | / | / |  | 5/19:待liang.zhao与 module owner，chao Gao;输出需求module list, schedule; 与PXP 一起讨论；
Certification |  |  | / | / | / | / | Display HDR 1400; DP1.4; HDMI2.1; AMD Free-sync; G-sync

## SoC BlockDiagram
See MS1 Bus spec

## Issue
SPEC | Y
SoC | Y
DataPath | Y
Pin Summary | Y
SW upgrade | Y
PLL CLK | Y
MEM MAP | Y
DFT | Y
LDC
Retiming
SCALER
HDR10
Sharpness
BCON
MPRT
OSD | Y
PowerDomain | Y
FPGA | ongoing
ULL | tsmc主推ULL，电压更低，速度与ULP相近
PINMUX
XIP